## Sheet1
Item | Deliverables | % of total project work | Time in hrs | Milestone cost
Landing page www.aatrral.com: search, Login Register, Roller image slider,Product listing |  |  | 9 Hours
Product detail page:Product detail page with tabs like Product detail with full information of the product, Ordering, etc. Order Noe button pdf/html ,product image and Product Video |  |  | 15 Hours
Product page Cont: search technical documentation listing |  |  | 4Hours
Design and Development: |  |  | 2 Hours
Ordering Page |  |  | 3 Hours
Download Page |  |  | 4 Hours
About Page |  |  | 1 Hour
Blog Page |  |  | 4 Hours
Forum Page |  |  | 4 Hours
Contact Page |  |  | 2 Hours